## Risks
<Project Name> Risk Assessment Version #
Organisation:
Project:
Author:
Creation Date:
| Risk Statement |  | Pre-mitigation Risk |  |  |  | Current Risk |  | Post-mitigation Risk |  |  |  | Post-Mitigation Risk
# | Condition | Consequence | Probability | Impact | Exposure | Code | Level | Mitigation | Probability | Impact | Exposure | Code | Level | Contingency | Triggers
1 | Illness/COVID | Unable to work on project, miss meetings | 60% | 8 | 4.8 | 3D | High | Maintain good hygiene | 30% | 5 | 1.5 | 2C | Low | Work remote, communicate with supervisors | Feeling unwell, exposure to illness in public space
2 |  |  | 35% | 7 | 2.45 | 2D | Medium |  | 10% | 5 | 0.5 | 1C | Very Low
3 |  |  | 30% | 7 | 2.1 | 2D | Medium |  | 10% | 5 | 0.5 | 1C | Very Low
4 |  |  | 25% | 8 | 2 | 2D | Medium |  | 12% | 4 | 0.48 | 1B | Very Low
5 |  |  | 30% | 6 | 1.8 | 2C | Low |  | 15% | 4 | 0.6 | 1B | Very Low
6 |  |  | 30% | 6 | 1.8 | 2C | Low |  | 15% | 4 | 0.6 | 1B | Very Low
7 |  |  | 25% | 6 | 1.5 | 2C | Low |  | 10% | 4 | 0.4 | 1B | Very Low
8 |  |  | 15% | 9 | 1.35 | 1E | Low |  | 5% | 5 | 0.25 | 1C | Very Low
9 |  |  | 0% | 0 | 0 |  | #N/A | [5 empty] | #N/A
10 |  |  | 0% | 0 | 0 |  | #N/A | [5 empty] | #N/A
11 |  |  | 0% | 0 | 0 |  | #N/A | [5 empty] | #N/A
12 |  |  | 0% | 0 | 0 |  | #N/A | [5 empty] | #N/A
13 |  |  | 0% | 0 | 0 |  | #N/A | [5 empty] | #N/A
14 |  |  | 0% | 0 | 0 |  | #N/A | [5 empty] | #N/A
15 |  |  | 0% | 0 | 0 |  | #N/A | [5 empty] | #N/A
16 |  |  | 0% | 0 | 0 |  | #N/A | [5 empty] | #N/A
17 |  |  | 0% | 0 | 0 |  | #N/A | [5 empty] | #N/A
18 |  |  | 0% | 0 | 0 |  | #N/A | [5 empty] | #N/A
19 |  |  | 0% | 0 | 0 |  | #N/A | [5 empty] | #N/A
20 |  |  | 0% | 0 | 0 |  | #N/A | [5 empty] | #N/A
How to use
Insert the Probability % and Impact value to calculate the Exposure, Code and Risk levels
Note on D8: Articulate the scale being used for probability inside of the parenthesis. E.g. (1-100%) Note: 100% would mean the item is no longer a risk and has become a problem.
Note on A9: Use this column as the risk identifier which, allows each risk to be uniquely identified.
Note on B9: Use this column to capture the "likely cause" of the risk. Be detailed enough so that you can start forming mitigation plans.
Note on C9: Use this column to capture the result of the risk, should it happen. If the consequences cannot be mitigated, you will have to dealt with them in a contingency plan.
Note on D9: Use this column to estimate the probability the risk will occur. Suggest using a percentage-based scale (1-99%).
Note on E9: Use this column to estimate the amount of impact or severity of the risk.
Note on F9: This column is computed as probability x impact. Once all risks have been entered, sort by this column to identify your biggest risks.
Note on I9: Use this column to document what plans the team has to prevent the risk or to reduce the impact before occurance. This may require creating a separate, more detailed plan.
Note on J9: Use this column to estimate the probability the risk will occur. Suggest using a percentage-based scale (1-99%).
Note on K9: Use this column to estimate the amount of impact or severity of the risk.
Note on L9: This column is computed as probability x impact. Once all risks have been entered, sort by this column to identify your biggest risks.
Note on O9: Use this column to identify what will need to be done if the risk becomes reality. This may require creating a separate, more detailed plan.
Note on P9: Use this column to identify what would prompt you to execute the contingency plan. A trigger is usually a date or some sort of threshold.

## Risk Matrix
Risk Matrix
Probability/Likelihood | Impact
| (A) Significant 1-2 | (B) Minor 3-4 | (C) Moderate 5-6 | (D) Major 7-8 | (E) Severe 9-10
(5) Almost Certain: >85% | 5A Low Exp: 0.85-1.7 | 5B Medium Exp: 2.55-3.4 | 5C High Exp: 4.25-5.1 | 5D Very High Exp: 5.95-6.8 | 5E Very High Exp: 7.65-8.5
(4) Probable: 66-85% | 4A Very Low Exp: 0.66-1.4 | 4B Low Exp: 1.98-2.8 | 4C Medium Exp: 3.3-4.2 | 4D High Exp: 4.62-5.6 | 4E Very High Exp: 5.94-7.0
(3) Possible: 41-65% | 3A Very Low Exp: 0.41-1.3 | 3B Low Exp: 1.23-2.6 | 3C Medium Exp: 2.05-3.9 | 3D High Exp: 2.87-5.2 | 3E High Exp: 3.69-6.5
(2) Unlikely: 15-40% | 2A Very Low Exp: 0.15-0.8 | 2B Very Low Exp: 0.45-1.6 | 2C Low Exp: 0.75-2.4 | 2D Medium Exp: 1.05-3.2 | 2E Medium Exp: 1.35-4.0
(1) Rare: <15% | 1A Very Low Exp: 0.05-0.3 | 1B Very Low Exp: 0.15-0.6 | 1C Very Low Exp: 0.25-0.9 | 1D Low Exp: 0.35-1.2 | 1E Low Exp: 0.45-1.5

## Probability Scale Definitions
Probability Scale Definitions
Level | Description | Percentage Range | Description
5 | Almost Certain | >85% | The event is expected to occur in most circumstances
4 | Probable | 66-85% | The event will probably occur in most circumstances
3 | Possible | 41-65% | The event should occur at some time
2 | Unlikely | 15-40% | The event could occur at some time
1 | Rare | <15% | The event may occur only in exceptional circumstances

## Impact Scale Definitions
Impact Scale Definitions
Level | Description | Percentage Range | Description
E | Severe | 9 - 10 | Catastrophic impact - Project failure, major deliverable loss, severe health/safety issues
D | Major | 7 - 8 | Significant impact - Major delays, substantial rework, significant resource issues
C | Moderate | 5 - 6 | Moderate impact - Schedule delays, some rework, moderate resource constraints
B | Minor | 3 - 4 | Minor impact - Small delays, minimal rework, minor resource issues
A | Insignificant | 1 - 2 | Negligible impact - No delays, minimal effect on quality or resources

## Events
<Project Name> Risk Assessment Version #
Organisation:
Project:
Author:
Date:
| Risk |  | Actual | Mitigation | Lessons
Date | Item | Event | Impact | Actions | Learned
Note on A10: Use this column as the risk identifier which, allows each risk to be uniquely identified.

## Possible Risks (hidden)
Possible Risks - (Use For Risk Identification)
Organization:
Initiative, Project, and/or Engagement:
Date:
Possible Risks | Designations | Action / Disposition of Concerns, Issues, and Problems
List possible risks identified from brainstorming, interviews, and/or risk knowledge bases | Designate a concern, issue, and problem with an X and Designate a risk with and R | Define the appropriate action for each item designated X in the previous column. Potential actions include "consolidate", "escalate", "refer", "restate", "treat as out of scope", or treat as a risk and change designation in previous column to an R

## Risk Identification (hidden)
Risk Identification - (Use For Risk Analysis and Prioritization)
Organization:
Iniative, Project, and/or Engagement:
Date:
Possible Risks | Identification Number | Classification / Category | Conditions | Consequences
Place the "R" designated items from the Possible Risks worksheet here | Use a number to uniquely identify each risk | • People - Customer - End User - Sponsors - Stakeholders - Personnel - Organization - Skills - Politics - Morale • Process - Mission and Goals - Decision Making - Project Characteristics - Budget, Costs, and Schedules - Requirements - Designs - Building - Testing • Technology - Security - Development and Test Environment - Tools - Deployment - Support - Operational Environment - Availability • Environmental - Legal - Regulatory - Competition - Economic - Technology - Business | Identify the cause of the risk | Define the potential result of the risk - there may be multiple consequences for each condition and some consequences can also be conditions

## Risk Analysis & Prioritization (hidden)
Risk Analysis and Prioritization - (Use For Risk Planning)
Organization:
Iniative, Project, and/or Engagement:
Date:
ID Number | Priority / Order | Probability (Numeric) | Impact (Numeric) | Exposure (Numeric) | Exposure Recipient (Text)
|  | Likelihood of the Risk Condition occurring, with 1% - 30% for low, 31% - 70% for medium, and 71% - 100% for high | Effect of the Risk Consequence, with 1 - 3 for low; 4 - 7 for medium, 8 - 10 for high, and 100 for catastrophic ratings | Calculated by multiplying Risk Probability times Risk Impact, and used as the basis for ordering and prioritizing Risks | Identify who will be affected by the risk exposure (e.g., Client, Partner, & Microsoft)

## Risk Planning (hidden)
Risk Planning - (Use For Risk Costing)
Organization:
Initiative, Project, and/or Engagement:
Date:
ID Number | Priority / Order | Mitigation Plans | Contingency Plans | Triggers | Responsible Person | Deliverables | Activities And Tasks | Dependencies | Time Frames | Due Dates | Resource Requirements
|  | Identify what must be done to reduce the probability of the risk condition occurring | Identify what must be done to reduce the impact of the risk consequence | Identify the criteria for determining when to initiate risk contingency plans | Identify the person responsible for each risk plan | Identify the deliverables that will be created by each risk plan | Identify the tasks and associated activities that will create the deliverables for each risk plan | Identify the tasks/activities that are dependent upon each other within each risk plan | Identify the start and complete dates for each risk plan | Identify the due date for each deliverable of the risk plan | Identify the skills, person hours, equipment, facilities, hardware, software and other resources needed for each deliverable of the risk plan (enter as individual and separate line items)

## Risk Costing (hidden)
Risk Costing
Organization:
Initiative, Project, and/or Engagement:
Date:
ID Number | Priority / Order | Resource Requirements | Resource Unit Cost | Resource Total Cost | Risk Plan Total Cost | Margin | Preferred Price | Competition Anticipated Price | Customer Anticipate Price | Proposed Price
|  | Identify the skills, person hours, equipment, facilities, hardware, software and other resources needed for each deliverable of the risk plan (enter as individual and separate line items) | The actual or estimated unit cost for each of the individual resource requirement line items | Calculate the total cost for each resource requirement line item. Multiply each individual resource requirement by its associated unit cost | Calculate the estimated total cost for implementing each risk plan. Add all resource total costs for each resource unit cost line item | Identify the desired return on investment for each risk plan, expressed as a percentage | Calculate the favored price to the customer in taking responsibility for and implementing each risk plan. Multiplying the margin percentage by the total cost for each risk plan and add the results to the total cost of each risk plan | Identify what competitors would charge the customer if they took responsibility for and implemented each risk plan | Estimate what the customer would consider an acceptable price for implementing each risk plan | Identify the price to be submitted to the customer to take responsibility for and implement each risk plan. Balance among the preferred price, competitive anticipated price, and customer anticipated price

## LookUp Table
Code | Risk Level | Change this accordingly to your needs if required :)
1A | Very Low
1B | Very Low
1C | Very Low
2A | Very Low
2B | Very Low
3A | Very Low
4A | Very Low
1D | Low
1E | Low
2C | Low
3B | Low
4B | Low
5A | Low
2D | Medium
2E | Medium
3C | Medium
4C | Medium
5B | Medium
3D | High
3E | High
4D | High
5C | High
4E | Very High
5D | Very High
5E | Very High

## Disclaimer
This is a hybrid risk assessment tool created by Adrian Lim W.S on 15th August 2025 Credits to Microsoft Risk Tool & Griffth University Enterprise Risk Management Matrix
Ó 2002 Microsoft Corporation. All rights reserved.
The information contained in this document represents the current view of Microsoft Corporation on the issues discussed as of the date of publication. Because Microsoft must respond to changing market conditions, it should not be interpreted to be a commitment on the part of Microsoft, and Microsoft cannot guarantee the accuracy of any information presented after the date of publication.
This document is for informational purposes only. MICROSOFT MAKES NO WARRANTIES, EXPRESS OR IMPLIED, IN THIS DOCUMENT.